## Sheet1
| Tasks | 2024-09-04 | 2024-09-18 | 2024-10-02 | 2024-10-16 | 2024-10-30 | 2024-11-13 | Legend | Completed
Status Update 1 | [8 empty] | In Progress
Oscilloscope and Multimeter | Completely working oscilloscope and multimeter | [7 empty] | Planned
Waveform Generator | Integrate bluetooth communication with mobile application | [7 empty] | Behind Schedule
PCB and Frame | Remove waveform generator, reduce board size
Mobile Application | Integrate bluetooth communication with waveform generator
Status Update 2
Oscilloscope and Multimeter | Oscilloscope capable of sending and receiving data via. bluetooth with App
Waveform Generator | Receive inputs from mobile app and storing data points
PCB and Frame | Assemble and test revised board, design pcb casing
Mobile Application | Integrate bluetooth communication with oscilloscope
Status Update 3
Oscilloscope and Multimeter | Multimeter capable of sending and receiving data via. bluetooth with App
Waveform Generator | Display waveforms on mobile app
PCB and Frame | Finish case, design any final board adjustments
Mobile Application | Integrate bluetooth communication with multimeter
Status Update 4
Oscilloscope and Multimeter | Testing integrated oscilloscope and multimeter
Waveform Generator | Smooth out graphs and test for accuracy
PCB and Frame | Implement final board adjustment and noise reduction methods, test 215 labs on board
Mobile Application | Debugg any application errors that may have appeared during integration
Status Update 5
Oscilloscope and Multimeter | Debugging, testing, and potential improvements
Waveform Generator | Debugging, testing, and potential improvements
PCB and Frame | Quality of life changes (size reduction, case aesthetics, price and noise reductions)
Mobile Application | Flesh out app GUI - Make the data presentation look good
Final Presentation
Oscilloscope and Multimeter | Prepare for Final presentation and Demo
Waveform Generator | Display accurate waveforms and bluetooth communication
PCB and Frame | Finalize and prepare for demo
Mobile Application | Showcase fully function app that communicates via Bluetooth with the final device