## Slide 1: Team 30: ECEN 215 Lab Kit Bi-Weekly Update 2 Members: Luis Diaz-Santini, Yusuf Hossain, Ryan Freed, and Peter Zhang Sponsor: Dr. Lusher TA: Garret Brown
Notes: Intro should take 30 seconds

## Slide 2: Project Summary
Problem Statement:
Principles of Electrical Engineering (ECEN 215) teaches the basics of electric circuit analysis and electronics to non-ECEN majors.
The transition of ECEN 215 to an online format poses a challenge due to its lab component relying on the Analog Discovery 2 (AD2), which is expensive.
Solution Proposal:
The ECEN 215 Lab Kit offers a solution to the cost, convenience, and over complication issues that are abundant with the AD2. Aiming for a $50 price point, the lab kit offers a more catered simpler approach to each lab while also making it possible to complete at home.
Will operate as the power supply, signal generator, multimeter, and Oscilloscope.

## Slide 3: Subsystems Overview
Peter: Multimeter and Oscilloscope
Yusuf: Waveforms and communicating to the microcontroller.
Luis: Mobile application to interface with device
Ryan: PCB design and power.

## Slide 4: Project Timeline
Ensure Working Subsystem (completed 8/22) | Research Integrating / Ensure Working Subsystems (completed 8/29) | Integrate App with Wave Gen and Oscilloscope (to complete by 9/24) | Integrate App with Multimeter (to complete by 10/16) | Complete Testing of Integrated Subsystems (to complete by 10/30) | Complete Validation of Integrated Subsystem (to complete by 11/7 | Documentation and Buffer Time (to complete by 11/10)

## Slide 5: Waveform Generator Yusuf Hossain
Accomplishments since last update 13 hrs of effort | Ongoing progress/problems and plans until the next presentation
Compacted all waveform shapes into 1 file without overloading ESP32 memory App is able to select between different waveform shapes | Resolve memory issues on the ESP32 with Wavegen function Work on displaying real time data for each waveform

## Slide 6: Mobile App Luis Diaz-Santini
Accomplishments since last update 17 hrs of effort | Ongoing progress/problems and plans until the next presentation
ESP32 successfully stores specific messages sent from application ESP32 can use the received messages to trigger actions | Solve memory issue with ESP32 Continue implementation of live oscilloscope graph displaying on application Determine which GPIOs to activate for power supply operation

## Slide 9: Oscilloscope and Multimeter Peter Zhang
Accomplishments since last update 12 hrs of effort | Ongoing progress/problems and plans until the next presentation
Updated design of ohmmeter and ammeter Redesigned bipolar voltage capabilities ESP32 sends messages which are stored in app | Implementation of real time plotting oscilloscope on application Combined code crashing

## Slide 10: Updated Designs

## Slide 11: PCB and Power Ryan Freed
Accomplishments since last update 34 hrs of effort | Ongoing progress/problems and plans until the next presentation
Received and assembled 80% of PCB Pushed multimeter changes onto Altium schematics | Touch up soldering paste issues Troubleshoot buck converters Push multimeter changes onto PCB

## Slide 13: 3.3 V test (top) and 5 V (bottom)

## Slide 14: Voltmeter (left) and Ammeter Switch (right)

## Slide 15: Ohmmeter (left) and Ammeter (right)

## Slide 16: Parts Ordering Status
  Ordering ADC by tomorrow
  Ordering amplifiers
  Ordering resistors and other small components
Notes: Michelle

## Slide 17: Execution Plan
Notes: Michelle

## Slide 18
Thank you